## Full Risk Register
IN CONFIDENCE - Working Draft
|  |  | North West London Elective Orthopaedic Centre OBC: Project Risk Register | [6 empty] | Date updated: | 2023-02-22
Ref. | Risk Category | Programme Theme | Risk Description | Likelihood (1-5) | Consequence (1-5) | Risk Rating | Mitigating Actions | Likelihood (1-5) | Consequence (1-5)2 | Risk Rating3 | Risk Owner | Next Review Date | Date last updated | Direction of travel | Status | Comments
R002 | Financial | Design/mobilisation & service change governance | There is a risk of insufficient capital funding to support the required theatre expansion and other infrastructure changes | 4 | 4 | 16 | TIF capital funding secured based on the OBC requirement. If the programme exceeds TIF time thresholds, potential to allocate capital via LNWH agreed in principle. Control of implementation costs via governance structure. See digital enablement risk | 3 | 3 | 9 | LNWH CFO | 2023-01-20 | 2023-01-20 |  | Open
R029 | Operational | Design/mobilisation | Risk that delay results in continuation of relatively low scores on clinical outcome metrics | 4 | 4 | 16 | Start to make changes prior to the new EOC opening, for example, Joint Weeks. Robust EOC programme governance and monitoring via Programme Board and Acute Provider Collaborative governance. Clinical leadership, use of best practice guidance and data through the design, development, and implementation phases across the programme governance. | 3 | 4 | 12 | NWL EOC Clinical Workstream Chair | 2023-01-20 | 2023-01-20 |  | Open
R038 | Financial | Design/mobilisation | There is a risk that energy and other supply chain pressures will affect project timelines and costs | 4 | 4 | 16 | Monitor and ensure early procurement of items where appropriate. Review of supply chains as per Secretary of State for Health instruction. Increase optimism bias from 15% to 23% in financial model | 3 | 4 | 12 | NWL EOC Estates Lead | 2023-01-20 | 2023-01-20 |  | Open
R004 | Operational | Design/mobilisation | There is a risk that elective recovery across surgical specialities continues to impact on capacity available for orthopaedics at CMH | 4 | 4 | 16 | LNWH RDG and executive led recovery programme. LNWH executive led weekly recovery delivery group Plan to recover LNWH and CMH BAU | 3 | 4 | 12 | NWL EOC Managing Director | 2023-01-20 | 2023-01-20 |  | Open
R006 | Operational | Design/mobilisation | There is a risk that delay to the project results in increased patient waiting times | 4 | 4 | 16 | Robust programme governance Ongoing surgical recovery plans Manage and mitigate risk to safe patient care through NWL Acute Providers and Acute Programme Governance including movement in orthopaedic PTL and ensure this is considered in decision-making going forward; Reassess PTL January 2023 Programme Board | 3 | 4 | 12 | NWL EOC Programme Board Chair | 2023-01-20 | 2023-01-20 |  | Open
R060 | Operational | Design/mobilisation | There is a risk that lack of clinical engagement with the EOC will result in under-utilisation of the EOC and unexpected pressure on the non-host trusts and NWL system | 4 | 4 | 16 | Undertaking from each Trust to contribute expected activity levels; EOC programme governance, mobilisation and centre management including MDT leadership; Risks and benefits, and supporting financial incentives, to be incorporated in mobilisation plans; Professional/medical director leads and EOC Managing Director support accordingly Clinical governance framework to measure and assure re service quality and outcomes | 3 | 4 | 12 | NWL EOC Programme Board Chair | 2023-01-20 | 2023-01-20 |  | Open
R016 | Strategic | Service change governance | There is a risk of public opposition to the proposed development of an elective orthopaedic centre. | 4 | 4 | 16 | Comprehensive engagement and involvement strategy to ensure user views inform the plan. Lay partner membership of the programme board and workstreams. Detailed and robust insights on the impact of all patient groups through a robust EHIA. Agreement by JHOSC to proceed with the informal engagement and involvement plan which is now underway. Public consultation will inform mitigation with co-design with stakeholders and JHOSC | 3 | 3 | 9 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R003 | Operational | Design/mobilisation & service change governance | There is a risk that the implementation is delayed by shortage of key staff groups and that staff experience is poor. Key retention and recruitment issues - covid recovery, T&Cs, numbers of staff, new roles and leadership capability. | 4 | 4 | 16 | CPO/executive led workforce workstream to develop staffing strategies, including recruitment drives, rotational posts, CPD Collaboration between all NWL acute trusts through the NWL ICS Acute Programme. Comprehensive engagement and involvement plan which includes all key stakeholder groups including staff communication, engagement, and consultation. Estates design focused on delivering an attractive and user-friendly environment, e.g. inclusion of staff facilities/rest room. Manage and mitigate risk to safe patient care through NWL Acute Programme Governance. | 3 | 4 | 12 | NWL EOC Workforce Chair | 2023-01-20 | 2023-01-20 |  | Open
R049 | Financial | Design/Mobilisation | EOC represents a significant uplift in beds, recovery areas and 2 additional theatres. There is a potential gap in expectation of IT infrastructure requirements. The baseline includes PCs networked (volume tbc) and Cerner project infrastructure for current bed base, recovery area and theatres. Neither The EOC or the Cerner business cases include device integration (BMDI and pumps) for ward and recovery areas, it is only funded for HDU and Critical Care. | 5 | 3 | 15 | Submit TIF bid for capital funding – awaiting outcome due 31/7/22 then re-score. Establish list of "must haves" for pre-Cerner and post Cerner implementation. The EOC infrastructure needs to be sourced to a safe level and as a minimum be consistent with other LNW & THH areas when Cerner is implemented. Establish the gap and if any further funding sources are available to bridge gaps / provide integrated for BMDI and Infusion management pumps? Update 16/01/2023: TIF bid unsuccessfu. The approach to solve the cost pressure within the Cerner Programme Business Case agreed with the LNW CFO. | 2 | 3 | 6 | NWL EOC Digital Workstream Chair |  | 2023-01-20 |  | Open
R064 | Operational | Design/Mobilisation | 2.There is a risk of EOC being reliant on the ICB Community elements of Digital Inclusion Plan. The ICB wide Digital Inclusion Planning Working Group was paused and is recommencing in April 2023. There is an interdependency for EOC to be able to use the ICB infrastructure and resources to support the digital inclusion in the Community. | 5 | 3 | 15 | Discussed at the ICS EOC Service Change Governance Project Delivery Group. To form part of the wider ICB equity plan and therefore EOC specific digital inclusion will ensure all processes have a digital and an equal non digital flow. Using existing solutions and maximising the benefits of existing and future digital inclusion projects with partner organisations | 3 | 3 | 9 | NWL EOC Digital Workstream Chair |  | 2023-01-20 |  | Open
R037 | Financial | Design/mobilisation | There is a risk that the all "in scope" activity as clinically modelled and incorporated in the financial case will not be realised from the start due to clinical caution, resulting in lower activity than expected | 4 | 3 | 12 | Clinical engagement and design governance through Clinical Design workstream Proposed new centre would be supported by robust clincial and operational governance including patient experience, outcomes and access | 2 | 3 | 6 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R052 | Clinical Care | Design/Mobilisation | There is a risk that non-adherence to the clinical model will result in a fragmented, inefficient service | 4 | 3 | 12 | Agreement to the clinical model via Clinical Design & Development workstream and EOC Programme Board; EOC management structure appointed in advance of opening | 3 | 2 | 6 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R053 | Clinical Care | Design/Mobilisation | There is a risk that waiting times will be inequitable within the EOC resulting in long waits for some patients and poor host trust RTT performance | 4 | 3 | 12 | Monitoring of waits per trust and per surgeon via EOC performance framework; Agree process for pooling/temporary reallocation of theatre capacity | 2 | 3 | 6 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R054 | Clinical Care | Design/Mobilisation | There is a risk that discharge pathways are not standardised across boroughs, resulting in delayed and inefficient discharge | 4 | 3 | 12 | Monthly engagement with MSK clinical network; Engagement with community partners; Discharge SOPs to be signed off by community partners; Oversight of discharge pathway via EOC clinical governance; Informed by MSK procurement process | 3 | 2 | 6 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R055 | Financial | Design/Mobilisation | Initial Digital budget may not be fit for purpose to enable the scaling up of the digital agenda against the initial budget included in the project development costs | 3 | 4 | 12 | Review and assess of potential developments that can be progressed to support mobilisation of the EOC ensuring that all charges in scope exclude and BAU schemes already in train Classify costs under the headings of necessary, nice to have and optimal | 2 | 4 | 8 | NWL EOC Digital Workstream Chair |  | 44946 |  | Closed - duplicate
R018 | Construction/Estates | Design/mobilisation | There is a risk that the implementation is delayed by longer than expected building time scales, including logistical challenges of building in a live environment | 3 | 4 | 12 | RIBA Stage 4 completed. Dedicated capital/project design sub-group and project manager to be appointed. Regular engagement with other site users and PFI Selection of contractor with experience of healthcare building in live environment Detailed planning of works, e.g., screening placement; plans for noisy works Formal liaison meetings with construction team and dedicated clinical/operational lead Oversight by LNWH contact lead of PFI contract. | 2 | 3 | 6 | NWL EOC Estates Lead |  | 2023-01-20 |  | Open
R042 | Strategic | Service change governance | There is a risk that a single specialty focus could potentially impact opportunities in wider surgical system re- design | 3 | 4 | 12 | Ensure centre design offers flexibility in use and consolidation addresses reported “land lock” in theatres and/ or within clinical pathways and required adjacencies. Green site deep dives launched with to identify opportunities to increase productivity and potential stepped increases capacity under Theatre Utilisation Improvement Project | 2 | 4 | 8 | NWL EOC Joint Senior SRO |  | 2022-12-13 |  | Open
R031 | Operational | Design/mobilisation | Patient transport costs are higher than current levels provisioned in OBC due to impact on patient travel requirements NWL ICB risk. NEPTS provision is a national framework | 3 | 4 | 12 | Obtain better understanding of patient transport requirements through patient engagement. Provision of patient information regarding travel arrangements and availability of sufficient car parking. Potential renegotiation of the transport contract across the Sector. | 2 | 4 | 8 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R025 | Construction/ Estates | Design/mobilisation | There is a risk that the displaced outpatient clinic and admin space cannot be accommodated satisfactorily at CMH without delaying the programme | 3 | 4 | 12 | Relocate neuro clinic by May 23 Utilise unoccupied space elsewhere in CMH where feasible Develop agile working solutions where feasible Map therapies pathway to space plan Project group reporting to Site Service Development Steering Group overseeing the relocation | 2 | 3 | 6 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R007 | Clinical Care | Design/mobilisation | There is a risk that the planned number of cases per list is not achieved | 3 | 4 | 12 | Implement best practice pathways supported by effective resources, training & development and advanced operational intelligence Clinical and operational agreement across partnerships and standing operational policies Engagement of clinical staff in solutions | 2 | 4 | 8 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R044 | Operational | Design/mobilisation | There is a risk that activity planning assumptions are not met between PCBC/OBC and implementation resulting in higher than expected waiting list pressures | 3 | 4 | 12 | Implement a high volume low complexity solution for orthopaedic surgery in NWL | 2 | 3 | 6 | NWL EOC Programme Board Chair |  | 2023-01-20 |  | Open
R001 | Strategic | Service change governance | There is a risk that ICB or partner trusts will not support the development or will prioritise other developments | 3 | 4 | 12 | Engagement throughout design & proposal development stages. PCBC approved by NWL ICB and OBC approved through all acute partner trust governance structures. Formally linked into development of all relevant system strategies including NWL ICS Acute, Population Health, Acute Strategy and Estates Strategy. NWL EOC Programme Board in place with all partners and disciplines represented. Capital is allocated. | 2 | 4 | 8 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R030 | Strategic | Design/mobilisation | Assumptions in theatre activity modelling vary significantly from actual demand. BMI not currently included. | 3 | 4 | 12 | Cross checking against sector-wide modelling assumption and review by the MSK Clinical Reference Group and the EOC Clinical Reference Group. In scope activity reviewed by Finance and Clinical Design workstreams | 2 | 2 | 4 | NWL EOC Programme Director |  | 2023-01-20 |  | Closed
R039 | Operational | Design/mobilisation | Lack of a single digital patient pathway platform results in resource-heavy, inefficient management of patient pathways between organisations | 4 | 3 | 12 | Managed by Digital workstream with regular updates to NWL EOC Programme Board Implementation of sector-wide digital platforms | 3 | 3 | 9 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R041 | Strategic | Service change governance | In addition to patient and stakeholder engagement/communication for this proposed service change, public consultation will be a requirement for a service change of this significance, and we will need key stakeholder input and support for when and how best this should happen. There is a risk that the process will be subject to judicial review | 3 | 4 | 12 | Now following NHSE Major Service Change policy and currently in public consultation with a programme that includes engagement of local authorities and final decision-making through the NWL ICB under a decision-making business case. | 2 | 4 | 8 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R043 | Strategic | Service change governance | There is a risk that the development of the centre has unintended consequences impacting on inequalities and equity of access and poor patient experience | 3 | 4 | 12 | Following the NHSE Major Service Change policy including equality impact assessment and integrated impact assessment. Following public consultation, decision making phase will include refresh of EIA and IIA | 2 | 4 | 8 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R045 | Strategic | Service change governance | There is a risk that opportunities for improved end-to-end musculoskeletal pathways have not been fully built into the model | 3 | 4 | 12 | Continued engagement with NWL ICB MSK leads and implementation of NWL MSK transformation plan | 2 | 3 | 6 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R036 | Financial | Design/mobilisation & service change governance | Significant increase in workforce to be based on the CMH site which if not filled with subtainial recruitment then temporary staffing will be attracted at a higher cost | 4 | 3 | 12 | Agency premium has been factored in based on LNWH's current recruitment profile Engagement and co-design of workforce plan with stakeholders Sensitivity analysis in the OBC will reflect the risk to savings based on greater reliance on temporary staffing | 3 | 3 | 9 | NWL EOC Workforce Chair |  | 2023-01-20 |  | Open
R040 | Financial | Design/mobilisation | There is a risk that the lack of a joint procurement strategy results in higher non-pay costs than necessary | 3 | 3 | 9 | NWL ICS Partnership Board to agree a procurement strategy ahead of implementaiton | 2 | 3 | 6 | LNWH CFO |  | 2023-01-20 |  | Open
R010 | Strategic | Design/mobilisation | There is a risk that lack of clinical engagement with the EOC will result in under-utilisation of the EOC and unexpected pressure on the non-host trusts | 3 | 3 | 9 | Undertaking from each Trust to contribute expected activity levels; Clear activity agreement between providers in Acute Care Collaborative; EOC management structure appointed in advance of opening; EOC clinical/medical director to engage with all surgeons; Clinical governance framework to measure and assure re service quality, outcomes & performance | 2 | 3 | 6 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R017 | Operational | Design/mobilisation | There is a risk that the planned bed capacity is insufficient due to longer than expected length of stay | 3 | 3 | 9 | Dedicated sub-group to focus on clinical pathways 7 day per week therapy staffing included in business case Joint school to prepare patients for surgery Work with NWL MSK team on pathway Develop SOPs for longer than expected lengths of stay | 2 | 3 | 6 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open | Review/close?
R056 | Clinical Care | Design/Mobilisation | There is a risk that the EOC clinical governance framework is not sufficiently robust, or not aligned across the partner trusts, resulting in gaps in assurance and potential patient harm | 3 | 3 | 9 | Establish clinical governance framework ahead of opening; Regular partnership board meetings to be established to oversee the management and governance of the EOC | 2 | 2 | 4 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R059 | Clinical Care | Design/Mobilisation | There is a risk that selection of patients for the EOC will be inadequate, resulting in higher than expected referrals back to home trusts, leading to patient dissatisfaction and delay | 3 | 3 | 9 | SOPs to be developed for patient selection, pre-operative assessment, referral back to home trust; Monitoring of rejections via clinical governance framework | 2 | 2 | 4 | NWL EOC Clinical Workstream Chair |  | 2023-01-20 |  | Open
R050 | Financial | Design/Mobilisation | Risk if there are late changes to the building design causing delays and cost implications for networking and WIFI | 3 | 3 | 9 | Agree date with technical, Cerner and Procurement team as to cut off date and communicate to relevant stakeholders | 2 | 3 | 6 | NWL EOC Digital Workstream Chair |  | 2023-01-20 |  | Open
R051 | Operational | Design/Mobilisation | Potential risk to staff engagement and of errors if the opening of EOC on legacy systems is close to the Cerner Implementation | 3 | 3 | 9 | Agree strategy for managing EOC go live on legacy systems, with support in place for staff not used to these and then further support with clear communication for Cerner implementation | 2 | 3 | 6 | NWL EOC Digital Workstream Chair |  | 2023-01-20 |  | Open | Change risk owner?
R008 | Construction/ Estates | Design/mobilisation | There is a risk that storage is insufficient resulting in poor processes and delays to care | 3 | 3 | 9 | Redesign storage areas in advance of opening to maximise use of space Rationalise products Involve clinical care in solutions Agree supply chain solution | 2 | 3 | 6 | NWL EOC Estates Lead |  | 2023-01-20 |  | Open | Close?
R028 | Construction/ Estates | Design/mobilisation | Potential risk of delay or cost increases due to availability of materials and/or supply chain constraints | 3 | 3 | 9 | Continuous dialogue with PFI Project Co Plan for early procurement of materials | 2 | 3 | 6 | NWL EOC Estates Lead |  | 2023-01-20 |  | Open
R033 | Financial | Service change governance | There is a risk that the calculated savings would not be realised in a timely manner if the inter trust marginal payment mechinism is in situ for a prolonged period | 3 | 3 | 9 | Ensure that marginal rate agreement is agreed for a fixed period to provide incentive to repurpose vacanct space | 2 | 3 | 6 | NWL EOC Finance Lead |  | 2023-01-20 |  | Open
R034 | Financial | Design/mobilisation & service change governance | Calculation of optimism bias at 15% doesn't provide sufficent mitigation to capital financial risk | 3 | 3 | 9 | Third stage costings have been used to inform the OBC including an allowance for heightened price inflation in addition to the 15% OB | 2 | 3 | 6 | NWL EOC Finance Lead |  | 2023-01-20 |  | Closed
R035 | Financial | Design/mobilisation | Variation in capital equipment requirements may emerge at implementaiton risking an overshoot of the current planned budget | 3 | 3 | 9 | Equipment capital budget has been included based on best expected cost at the time fo writing the OBC Optimism bias at 23% | 2 | 4 | 8 | NWL EOC Finance Lead |  | 2023-01-20 |  | Open
R005 | Financial | Design/mobilisation | There is a risk that the management /admin costs and strutcure in the business case are too low given the nature of the EOC partnership | 3 | 3 | 9 | Informed in FBC by host's proposed management structure Review grade-mix within budgeted cost | 2 | 2 | 4 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R061 | Operational | Design/mobilisaiton | There is a risk that patients are unable to access services at the centre due to transport difficulties, both physical and financial. NWL ICB risk. NEPTS provision is a national framework | 3 | 3 | 9 | Travel analysis included in the integrated impact assessment, which identifies key risk groups, namely deprived and elderly/disabled populations. Transport options will be explored alongside learning from other centres. | 2 | 2 | 4 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R048 | Strategic | Service change governance | Risk that variation in HCAS for inner and outer London results in more vacancies than modelled | 3 | 3 | 9 | As with other specialist centres it is expected that staff will remain employed on existing terms A significant proportion of staff will be recruited to the EOC on local terms | 2 | 3 | 6 | NWL EOC Workforce Chair | 2023-01-20 | 2023-01-20 |  | Open
R065 | Operational | Design/Mobilisation | There is risk of sharing patient Waiting List and clinical information before LNW and THH go live with Cerner | 3 | 3 | 9 | THH and LNW input in the Inter Trust Referral Working Group. All NWL acute trusts have signed up to use the Care Coordination System for sharing patient waiting list information. All systems capabilities and data sources are being regularly reviewed to ensure the workflow supports both Cerner, Silverlink PAS and Newton to meet the Minimum Data Set criteria. | 1 | 3 | 3 | NWL EOC Digital Workstream Chair |  | 2023-01-20 |  | Open
R066 | Operational | Design/Mobilisation | There is a risk of the existing LNW admin teams being overloaded by the process of patient transfer into EOC causing delays to treatment. | 3 | 3 | 9 | Discussion with M. Titcomb to ensure clarity on the workflow, roles and responsibilities and resourcing to an appropriate level to enable safe transfer of patients. Centralised hub model business case, potentially as a wider initiative for mutual aid and all ICB hubs | 2 | 3 | 6 | NWL EOC Digital Workstream Chair |  | 2023-01-20 |  | Open
R014 | Construction/ Estates | Design/Mobilisation | There is a risk of delay or cost increase due to PFI Project Co taking longer to make decisions than planned (e.g., stage 3 & 4 delays), requiring significant change, or getting lenders' approval | 2 | 4 | 8 | Weekly assurance meeting to address issues as they arise Successful track record of working with PFI Project Co Non-adversarial relationship is continued with early engagement. OBC includes 23% optmism bias. LNWH PFI Co Contact Lead advised and lead CFO for project. | 1 | 4 | 4 | NWL EOC Estates Lead |  | 2023-01-20 |  | Open
R011 | Financial | Design/mobilisation | There is a risk that COVID-19 swab costs of £25 per swab increase the cost of delivery of POA such that the service cannot break even when top up funding is removed | 4 | 2 | 8 | Highlight the cost impact Negotiate cost avoidance with ICS Ensure that financial model reflects most recent guidence on COVID testing requirements | 3 | 2 | 6 | NWL EOC Finance Lead |  | 2023-01-20 |  | Closed
R013 | Strategic | Service change governance | Other services take priority on the CMH site resulting in lack of space to accommodate the EOC | 2 | 4 | 8 | Agreed priority though Acute Programme Board Overseen by LNWH site strategy group Led by CMH Managing Director | 1 | 4 | 4 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R009 | Clinical Care | Design/mobilisation | There is a risk that orthopaedic patients requiring Enhanced Care Unit (ECU) care will not have access to a side room when needed | 2 | 4 | 8 | Develop standard operating policies to address ECU capacity pressures Plan ECU admission pre-operatively wherever possible | 1 | 4 | 4 | NWL EOC Managing Director |  | 2023-01-20 |  | Closed. Merge w. R021
R012 | Clinical Care | Design/mobilisation | There is a risk of compromised infection control due to co-location of other specialities | 2 | 4 | 8 | Allocation of sufficient capacity through demand & capacity modelling Design of ring-fenced pathways and centre design, with ACAD to be used by pre-operative and day case pathways only Standard operating policies for all aspects of the pathway Risk assessment by infection control team Sign off by Chief Nurse | 2 | 2 | 4 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R015 | Operational | Service change governance | There is a risk that the disaggragated nature and/or sparsity of managers to input in a timely way to the project will result in delays to the project | 4 | 2 | 8 | Potential allocation of additional resource from within NWL | 3 | 2 | 6 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R057 | Financial | Design/Mobilisation | There is a risk that the framework for clinical supplies is not agreed, or delayed, resulting in patient cancellation and increased cost | 2 | 4 | 8 | Establish a clinical supplies framework via the Clinical Design and Finance workstreams, to be in place before opening; Oversight and regular review of framework via EOC management | 1 | 3 | 3 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R046 | Strategic | Service change governance | Potential re-design and/or significant adjustments to workforce model required post public consultation | 2 | 4 | 8 | Evidence based design Engagement & Involvement Plan(pre public consultation) | 1 | 2 | 2 | NWL EOC Programme Director |  | 2023-01-20 |  | Open | Lead changed
R026 | Construction/ Estates | Design/mobilisation | Risk to the project timeline if sutiable and avilable temporary recovery soultions are not developed in a timely manner. | 2 | 4 | 8 | Agree temporary recovery plan with colorectal services, including infection control, fire, facilities teams. Complete risk assessment Schedule dummy run; confirm costing | 1 | 4 | 4 | NWL EOC Transformation Lead |  | 2023-01-20 |  | Open | Original score amended at CDW mtg 9/12/22
R067 | Financial | Design/Mobilisation | Activity in scope of the EOC based on validated submissions from host and home Trusts has communicated a 7 - 11% data validation gap in the baseline activity included in the EOC | 4 | 2 | 8 | Growth in the NWL sector PTL supports that across the sector there is sufficent activity to occupy validation difference | 2 | 2 | 4 | LNWH CFO |  | 2023-01-20 |  | Open
R062 | Strategic | Design/mobilisation | Increased travel times for some patients will result in a marginal increase in CO2 emissions. | 3 | 2 | 6 | The impact is measured as marginal and likely to be mitigated by established green projects | 2 | 1 | 2 | LNWH CFO |  | 2023-01-20 |  | Open
R032 | Construction/ Estates | Design/mobilisation | There is no space for a bed hold | 3 | 2 | 6 | Review patient flow to identify solutions | 3 | 1 | 3 | NWL EOC Estates Lead |  | 2023-01-20 |  | Closed
R022 | Financial | Service change governance | There is a risk that an approach to stranded costs will not be agreed and that Trusts will consider the financial risk too high | 2 | 3 | 6 | Approach to be discussed in detail at an early stage with ICS partners | 1 | 3 | 3 | NWL EOC Finance Lead |  | 2023-01-20 |  | Open
R020 | Operational | Design/mobilisation | There is a risk that the patient pathway is compromised by shared use of clinical areas in ACAD for admissions and day surgery | 3 | 2 | 6 | Map patient pathway to identify and address pinch points Transform admission process to allow staggered admissions (two admission times per day) | 2 | 2 | 4 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R021 | Clinical Care | Design/mobilisation | There is a risk that capacity for critical care level 1 and 2 patients is insufficient | 2 | 3 | 6 | Modelling based on clinical evidence Build in ability to flex capacity Agree clinical model of ASA1 & 2 only Develop standard operating policies to address ECU capacity pressures Plan ECU admission pre-operatively wherever possible | 1 | 3 | 3 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R058 | Operational | Design/Mobilisation | There is a risk that patients will be reluctant to have surgery at the EOC resulting in under-utilisation or patient dissatsifaction | 2 | 3 | 6 | Robust public engagement during and after public consultation; Explanatory patient/GP communications available; Clear EOC statement on patient choice | 1 | 2 | 2 | NWL EOC Managing Director |  | 2023-01-20 |  | Open
R019 | Strategic | Service change governance | There is a risk that partner organisations are not aligned on a partnership model and that this results in delayed governance | 2 | 3 | 6 | Early engagement in line with ICS Multi-Organisational System Financial Framework Governance via EOC Programme Board | 1 | 3 | 3 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R023 | Strategic | Service change governance | There is a risk that a lengthy period between OBC and FBC delays implementation | 3 | 2 | 6 | Ongoing engagement with Acute Programme Board Good project governance | 2 | 2 | 4 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R024 | Strategic | Service change governance | There is a risk that the Ultra Low Emission Zone charge will generate public opposition to the development | 3 | 2 | 6 | Travel analysis as part of public engagement and decision making Communication strategy to address ULEZ | 2 | 2 | 4 | NWL EOC Programme Director |  | 2023-01-20 |  | Open
R047 | Strategic | Service change governance | Risk that staff stakeholder engagement is inadequate and delays development and implementation of workforce plans | 3 | 2 | 6 | NWL ICS Acute Programme and NWL ICS EOC Board support to develop and progress initial, informal engagement with stakeholders | 2 | 2 | 4 | NWL EOC Workforce Chair |  | 2023-01-20 |  | Open
R063 | Strategic | Service change governance | Risk that with majority of staff now likely to remain with providers, failure to identify alternative activity could lead to staff being at risk of redundancy | 3 | 2 | 6 | Two of the three trusts have identified alternate activity, whilst one of the trusts is currently working to identify alternate activity | 2 | 2 | 4 | NWL EOC Workforce Chair |  | 2023-01-20 |  | Open
R027 | Operational | Design/Mobilisation | There is a risk that the proposed Pre-operative Assessment (POA) pathway improvements will not be achieved resulting in a c£190k overspend | 2 | 2 | 4 | Dedicated project to deliver POA pathway improvements Link to LNWH wider POA transformation | 2 | 2 | 4 | LNW Surgical DDO |  | 2023-01-20 |  | Open | NEW RISK
R068 | Operational | Design/Mobilisation | The blood transfusion policies within the individual trusts to ensure National standards met, require "group and save" to be completed with all data items matching. Because each organisation has different local MRNs this causes a risk of delay in surgery as TDL pathology system will only recognise local MRNs | 4 | 4 | 16 | Two options to mitigate the issue: 1. G&S done at admission in LNW with phlebotomy personnel in EOC admission area so nurses are not slowed down by taking bloods 2. All EOC patients POA done at LNW including G&S To be agreed with ICS Ways of Working Programme and POA ICB Working Group | 2 | 4 | 8 | NWL EOC Digital Workstream Chair |  | 2023-02-21 |  | Open
R069 | Operational | Design/Mobilisation | Different Cerner MRNs may cause issues in looking up information in Downstream Systems, ie. PACS.There is a risk If imaging is done at home Trust, these will not be available in LNW for intervention and vice versa for follow ups. | 4 | 4 | 16 | PACS sharing via IEP. Cross organisation workflow for uploading images needs to be agreed. Two options: 1. Centralised team of staff with access to all Trusts PACS will manage the IEP upload from the referring Trust to EOC and from EOC back to Referring Trust 2. Each Trust Radiology Department is responsible for their individual upload to IEP The amount of additional work needs to be modelled to understand impact on staff workload | 2 | 4 | 8 | NWL EOC Digital Workstream Chair |  | 2023-02-21 |  | Open
R070 | Operational | Design/Mobilisation | Risk of clinical records stored in Electronic Document Management systems not viewable across Organisations. MediViewer, CDL and Evolve records need to be visible to all four Organisations. | 4 | 4 | 16 | Work with software suppliers to enable cross oranisation viewing of documents using context link | 2 | 4 | 8 | NWL EOC Digital Workstream Chair |  | 2023-02-21 |  | Open
R071 | Operational | Design/Mobilisation | Risk of inability to view and confirm eConsent across organisations as LNW will not be live with eConsent by the proposed opening time of EOC | 4 | 3 | 12 | Work with Concentric to review and access potetial developments of surgeon confirming eConsent whilst in non-eConsent organisation. Workflow to be agreed in ICS ways of working group. EOC workflows potentially will need to manage a hybrid of paper consent forms for LNW and THH in the short term and eConsent from ICH and CW | 3 | 3 | 9 | NWL EOC Digital Workstream Chair |  | 2023-02-21 |  | Open

## Key
Likelihood |  | Consequence |  |  |  | Risk Owners
5 | Almost certain | 5 | Catastrophic |  |  | NWL EOC Programme Director | Martina Dineen
4 | Likely | 4 | Major |  |  | LNWH CFO | Jonathan Reid
3 | Possible | 3 | Moderate |  |  | NWL EOC Managing Director | Mark Titcomb
2 | Unlikely | 2 | Minor |  |  | NWL EOC Clinical Workstream Chair | Jon Baker
1 | Rare | 1 | Negligible |  |  | NWL EOC Transformation Lead | Chloe Cox
[6 empty] | NWL EOC Estates Lead | Gary Munn
[6 empty] | NWL EOC Clinical Advisor | Ian Holloway/ Matt Bartlett
|  |  |  | Risk Rating |  | NWL EOC Finance Lead | Wendy Harrowell/Shekh Motin
|  |  |  | 15+ | High | NWL EOC Data Lead | Piers Milner
|  |  |  | 8 to 12 | Medium | NWL EOC Facilities Lead | Yvonne Smith
|  |  |  | 4 to 6 | Low | NWL EOC Workforce Chair | Kevin Croft
|  |  |  | Below 4 | Minimal | LNW Surgical DDO | Kevin Finlinson
[6 empty] | NWL EOC Digital Workstream Chair | Kevin Jarrold
[6 empty] | NWL EOC Joint Senior SRO | Pippa Nightingale & Tim Orchard
[6 empty] | NWL EOC Programme Board Chair | Roger Chinn
| Risk Categories |  | Programme Themes
| Strategic |  | Design/mobilisation
| Clinical Care |  | Service change governance
| Operational |  | Design/mobilisation & service change governance
Financial
Construction/ Estates

## Change Control Process
1 | Updating, and managing the mitigation of, each risk is the responsibility of the named lead
2 | Any changes to be signed off by the named lead
3 | New/revised risks scoring over 15 to be presented at NWL EOC Programme Board by named lead
4 | Risks 15 and above and new risks to be discussed at NWL EOC Programme Board
5 | Risks 12 and above to be programmed for discussion at an appropriate future NWL EOC Programme Board